## DEV - DONE
NPDC Matillion Migration and Upgrade 1.68.7 to 1.72.4
Project Phases and Schedule |  |  | Status | QRIOUS Team |  | NPDC Team |  | Workflow - Jira Board:
Ph1: Planning - Ends Jan 26th |  |  | DONE | Managing Consultant: | Scott McKay <Scott.McKay@qrious.co.nz> | Project Sponsor: | Jan Holdt <Jan.Holdt@npdc.govt.nz> | Link Here
PH2: Migration to Dev Instance - Jan 29th to Feb 2nd, 2023 |  |  | In Progress | Delivery Lead: | Sharon Alabastro <Sharon.Alabastro@qrious.co.nz> | NPDC Project Manager: | Carrie Taylor <Carrie.Taylor@npdc.govt.nz>
Ph3: Migration to TEST and PROD - Feb 5th to 9th (Feb 12 - 16) |  |  | In Progress | Solutions Architect: | Sandeep Gainda <Sandeep.Gainda@qrious.co.nz> | IT Sponsor | Storm Newland <Storm.Newland@npdc.govt.nz>
Ph4: Testing, Handover, Documentation - Feb 12th to 16th |  |  | Not Started | Senior Consultant: | Jianjun Dai <Jianjun.Dai@qrious.co.nz> | Product Owner: | Sandra Street <Sandra.Street@npdc.govt.nz> | Communications Channel - Teams Chat
|  |  |  | Senior Consultant: | Kay Wu <Kay.Wu@qrious.co.nz> | Data Engineer: | Connor Crowley <Connor.Crowley@npdc.govt.nz> | Link here
|  |  |  | MSE Lead: | Gary Sin <Gary.Sin@qrious.co.nz> | Data Engineer: | Donna Jolly <Donna.Jolly@npdc.govt.nz>
Holidays: Jan 22, WLG Anniv ¦ Jan 29, AKL Anniv ¦Feb 6th, Waitangi Day |  |  |  | Senior Engineer: | Manh Hoang Ha ManhHoang.Ha@qrious.co.nz | Security and Architecture SME​​ | Sean de Jager <Sean.deJager@npdc.govt.nz>
DEVELOPMENT ENVIRONMENT
Task# | Task | Owners | Status | Responsibilities / Expected Outcome |  | Effort / Duration (Hours) - DEV | Planned Completion Date | Completion Time | Comments or Next Sub-Actions (RACI) | LEARNINGS
|  |  |  | Qrious | NPDC
1 | Make sure the usage of following resources mentioned in https://docs.matillion.com/metl/docs/migration/ (DEVELOPMENT) | JJ and NPDC | DONE | Qrious to advise everyone when the official process starts. Create a Group Chat to allow for immediate cascading of information, question, and updates. (25 Jan: Kay to have a look) 25 Jan: JJ logged into NPDC Matillion and went through the list of items and discussed with Kay and Connor. In summary, after migration, we need to: 1) check Query Profile and Extract Profile between 1.68.7 and 1.72.4 to make sure they are identical. 2) check emerald.properties file to make sure it is identical. 3) check User Configuration / OpenID to make sure it is identical. For detail, refer to NPDC matillion upgrade | NPDC SME to advise if these resources are used. (Connor Crowley) | 1 | 2024-01-26 |  | Ensure Matillion software is up-to-date and compatible with the latest technologies and systems.
2 | Make sure the usage of following Matillion function: SQS queue, CDC, CDC task source creation (DEVELOPMENT) | JJ and NPDC | DONE | Qrios to Gather and integrate feedback from NPDC to continually enhance Matillion and its documentation. Check with Kay First, then check with Connor. Sharon to consolidate the IPs for whitelisting. 25 Jan: Kay confirmed that there is no use of queues, cdc, and cdc tasks. 25 Jan: Connor also confirmed that no use of these functions. | NPDC SME to advise if these resources are used. | 1 | 2024-01-26 |  | If NPDC confirms that these matillion functions are used, then additional tasks may need to be identified and added into the runsheet.
3 | Make sure all developers' changes are commited and push to the remote repo (DEVELOPMENT) | JJ and NPDC | DONE | Qrious to explain to NPDC that we are "Choosing migrate with GIT". This is the option when GIT is enabled, which is the case in NPDC. 25 Jan: JJ and Connor discussed this and agreed this is good practice. Connor is going to coordinate NPDC developers to commit and push to remote repo by Friday EOD. 26 Jan: Connor has communicated with the rest of the developers and all of the changes are now commited to GIT and pushed to remote depo. | NPDC SME to advise the developer team. | 8 | 2024-01-26 |  | NPDC (Connor) needs to be aware that this is coming his way, and ensure that all developers' changes are committed and pushed remote repo.
4 | Decide if we need to "Remove unnecessary versions in Matillion VM 1.68" | JJ and NPDC | DONE | 25 Jan: JJ and Connor discussed this and Connor suggested to retain all versions to run the migration process. In case of hitting issue during the migration process, we will revisit this option and possible reduce the number of versions by then. | NPDC SME to standby for questions., and identify the unncessary versions | 3 | 2024-01-26 |  | Unnecessary versions may slow down the migration process (https://community.matillion.com/s/question/0D5Tm000002hj2CKAQ/migrating-matillion-etl-1598-to-1730-but-migrate-utility-gets-stuck-help)
5 | Advise NPDC data engineer that Matillion upgrade on Dev will start. | JJ and NPDC | DONE | Qrious (Sharon) to inform NPDC. | NPDC SME to standby for questions. | 1 | 2024-01-30 | 10AM | Communication will be shared via Teams Chat
6 | Stop all Matillion jobs (during the entire process of the deployment; this is the start of the downtime) (DEVELOPMENT) | JJ and NPDC | DONE | Qrious needs to advise NPDC that this task will impact only the DEV environment, therefore the NPDC's "BAU" activities (PROD env) are still going to continue as usual. 29 Jan: JJ checked the Manage Schedule in Matillion Dev and all | 1. NPDC SME to standby for questions. 2. NPDC SME to inform Qrious of what these Matillion Jobs are (In the Matillion Hub). | 32 | 2024-02-02 | 1PM | This is in the DEV stage therefore there is no impact to Production. However, any activities that NPDC does in the DEV Environment will need to be stopped. Other tools like Snowflake Development Database will also be impacted.
7 | Backup Matillion VM 1.68 | Manh | DONE | This is not dependent on any NPDC actions, therefore, Qrious went ahead and did the backup. |  | 4 | 2024-01-22 | 1PM | Private IP: 10.0.1.4 - Public IP: 20.5.77.100 - Domain: dev-dp-matillion.australiaeast.cloudapp.azure.com
8 | Install new Matilion VM 1.72.4 | Manh | DONE | Qrious to inform NPDC when installation starts, and ends, and communicate the new VM IP Address. (IAC). There is no dependency with NPDC at this point so this task can commence. | NPDC SME to standby for questions. | 10 | 2024-01-31 | 4PM | Private IP: 10.0.1.5 - Public IP: 20.58.182.42 - Domain: dev-dp-matillion-02.australiaeast.cloudapp.azure.com
8.1 | Change Matillion VM 1.72.4 password for azure-user | Manh | DONE | Qrious to inform NPDC when this is done. | NPDC SME to standby for questions.
8.2 | Make sure the TCP/IP connection from Matillion VM 1.68 to Matillion VM 1.72 works | Manh | DONE | Manh to confirm with JJ. | NPDC SME to standby for questions.
8.3 | Make sure Matillion VM 1.72 is able to access artifacts.matillion.com | Manh | DONE |  | NPDC SME to standby for questions.
8.4 | Whitelist IPs address to port 443 and 22 | Manh | DONE
8.5 | Setup SSO for the new Matillion | Manh / NPDC | DONE | 30 Jan: Manh is investigating the setup detail for SSO. In the meantime, JJ is progressing with the migration WITHOUT migrate the user(as the 1.68.7 uses SSO, while 1.72.4 is using internal user at the moment) and the Matillion Migration Utility is not able to migrate the users automatically, we will manually migrate 11 users. https://docs.matillion.com/metl/docs/2945143/ | NPDC SME to standby for questions/ actions / access provision. |  | 2024-01-31
8.6 | Associate Matillion instance to Matillion hub account | JJ / NPDC | DONE | Need access to Matillion hub billing to do this 30 Jan: Jianjun uses his matillion hub access to try to add the new instance dev-dp-matillion-02.australiaeast.cloudapp.azure.com into hub, but unable to do it as his access does not have the privilege. 30 Jan: Connor assigned billing privilege to Jianjun and he completed the association of the new instance into NPDC Matillion Hub. The new instance name is dev_mtln_upgrd_de_dataplatform |  | 1
8.7 | Remove the instance shutdown restriction for both the 1.68.7 and 1.72.4 (currently between 5pm and 7am) in case if the migration process run over 5pm. | Manh | DONE | Removal of the restriction (setting in Azure VM). - Manh/ Connor | NPDC SME to standby for questions. |  | 2024-01-30 | 3PM onwards
9 | Clone Snowflake Dev database (eg. DEV_DWH_CLONE) (DEVELOPMENT) This is not planned for Production. If needed for TEST, we'll determine this after the DEV environment. | JJ | DONE | JJ to have Snowflake Access, we need to check with Kay how she does this before. How many DBs does NPDC have? Whitelisting… (25 Jan: Kay confirmed that NPDC has 1 DB for 1 environment) One database only DEV_DWH JJ to check the Data Retention Policies - Ideally have 7 days for data recovery (Time Travel Feature) 25 Jan: checked the time travel setting. DEV/TST DATA_RETENTION_TIME_IN_DAYS set to 1 for most of the objects with very small number of tables set to null. PRD DATA_RETENTION_TIME_IN_DAYS set to 10 for datastore and presentation schema, with the rest set to 1 (very small number of tables set to null) Refer to detail migration document for detail | NPDC SME to standby for questions. Connor to provide a list of DBs to clone. | 1 | 2024-01-26 |  | It took 56 minutes to clone the database DEV_DWH. This is recommended by Matillion and use for avoid impacting development team ongoing efforts
10 | Assign priviledges to the clone snowflake database to allow Matillion job running. | JJ and NPDC | DONE | Qrious to discuss with NPDC the priviledges assignment so these can be assigned accordingly. 29-Jan: Refer to worksheet 002_clone_dev_dwh in snowflake for the script. | NPDC SME to work closely with Qrious. | 3 | 2024-01-29
11 | Remove GIT from Matillion ETL 1.68.7 | Manh and JJ | DONE | 31 Jan: As per JJ > https://support.matillion.com/s/article/How-To-Removing-Git-From-A-Project |  |  | 2024-01-31
12 | Go to Matillion VM 1.68, Admin -> Migrate and follow the prompts (DEVELOPMENT) | JJ | DONE | Qrious to update the Matillion Process Document - Upgrade/ Migrate (add the sreenshot of the configuration pages). 30 Jan: I have managed to run the migration utility successfully (after removing 6 unneeded versions). When I went to the new 1.73.4 instance, it looks all the jobs are migrated (except 1 job showing in the error report). However, I noticed that the GIT configuration is not migrated as expected. I suspect this may due to currently we are using internal user rather than OpenID (SSO) in the new 1.73.4 instance as Manh is in the process of setting SSO. I have let Connor know of this issue and will also raise a support ticket to Matillion to seek their advice. Once we have SSO setup, I will re-migrate again to see if this solves the GIT issue. Matillion support case 00067947 is submitted with P1 priority. | NPDC SME to standby for questions. | 6 | 2024-01-30 |  | Follow the detail steps from https://docs.matillion.com/metl/docs/migration/#performing-the-migration Choose migrate with GIT Add screen shot of the configuration pages
13 | Configure GIT for Matillion 1.73.4 and perform a one-time commit of all jobs after the migrate | JJ and NPDC | DONE | According to Matillion document "When you perform a migration with Git enabled, commits for orchestration and transformation jobs in every project in the target instance will be flagged as Modified. You will need to perform a one-time commit of all jobs after the migrate, which will remove the Modified flag. This is expected behavior, due to some of the formats of the jobs changing during the upgrade, and isn't a cause for concern. These are valid changes to the structure of the jobs and you can commit them safely.", this task is to commit all these modified jobs to GIT. 31 Jan: completed the enable of GIT in the new 1.72.4 instance and try to commit changes. But, noticed in the new instance, there is no change need to be commited. Asked this question to Matillion support in Matillion support case 00067947. | NPDC SME to standby for questions. | 2 | 2024-02-07
14 | Update Matillion VM 1.72.4 projects' environment configurations on the new instance to refer to the cloned objects (development_clone) | JJ | DONE | Qrious to advice that NPDC processes in 1.68 PROD is still BAU, and no impact to their ongoing activities as these DEV changes are happening. 26 Jan: JJ to check with Kay for any file based load and see if we would like to replicate them as part of testing in DEV_DWH_CLONE. Connor is going to check with team to see if any script available for creating these stages as part of the original release process. 26 Jan: JJ checked with Kay and also searched across Matillion and found out the copy into command from matillion component (Azure Blob Storage Load) mostly use Azure file container URL directly rather than stage. (there are a few jobs refer to stage AZURE_STORAGE_STAGE) but they mostly archived jobs. Hence, we shall be able to kick out jobs with the DEV_DWH_CLONE database. 29 Jan: executed 013_setup_for_dev_dwh script in snowflake to update MDP tables target database name from DEV_DWH to DEV_DWH_CLONE. | NPDC SME to standby for questions. | 2 | 2024-01-31 |  | https://support.matillion.com/s/article/HowToUpgradeMatillionETLbywayofMigration
15 | Create version btg_dev_MatillionUpgrade in the upgraded Matillion Development environment (1.72.4), switch to this version and checkout dev_master from GIT to get ready for batch run testing. | JJ | DONE | This is to create a workspace in the upgraded Matillion environment with the production set of the code to get ready for batch run testing. | NPDC SME to standby for questions.
16 | Apply any customizations on the new instance that are not migrated via the Migrate utility (details here): (see task 1 Qrious Responsibility) | JJ | DONE | Qrious to refer to any feedback referring to Steps 1-3. | NPDC SME to standby for questions. | 2 | 2024-01-31
17 | Identify any breaking changes by validating and running ALL regularly scheduled workflows. | JJ and NPDC | DONE | Qrious to execute the workflows to detect any issue. 31 Jan: reported error of not able to migrate on scheduled job 000_orc_load all parking jobs. this schedule is flagged as error in 1.68.7 as the job does not exist. 01 Feb: executed all of the daily batch jobs in the Matillion 1.72.4 environment on Snowflake DEV_DWH_CLONE environment, except dj_00_orc_run_techone_daily, which currently takes 4hours and currently running. | NPDC SME to standby for questions. | 8 | 2024-02-01
18 | Remediate errors and warnings as needed. There are two approaches to fix them: 1. Fix in Matillion VM 1.68 and promote through dev, test and production. 2. Fix in Matillion VM 1.72 and take note of all fixes and re-apply to test and production during the migration process. | JJ and NPDC | DONE | Qrious to discuss with NPDC for any issues found during the job run and find solution for the remediation. 31 Jan: As no error jobs during the migration, this step is not applicable. | NPDC SME to standby for questions. | 8 | 2024-02-02
19 | Update Matillion VM 1.72 Environment(s) to refer to the live (DEV) environment rather than the clone one. (i.e development) | JJ | DONE | Qrious to make the configuration change in Matilion VM 1.72.4 | NPDC SME to standby for questions. | 1 | 2024-02-02
20 | In Matillion VM 1.72, run all regularly scheduled workflows against DEV_DWH database. | JJ and NPDC | DONE | Qrious to execute the workflows to detect any issue. | NPDC SME to standby for questions. | 8 | 2024-02-05
21 | Assign the new Matillion VM to access adls storage account | Manh | DONE | In order to give new Matillion VM access to adls storage account, the old VM will need to be removed the access to storage account
22 | Functional testing for Matllion VM 1.72: create user, create version, create jobs, git integration | JJ | DONE | Qrious to test the Matilion VM 1.72.4 functions. | NPDC SME to standby for questions. | 4 | 2024-02-05 |  | These testing items may be: • User • Version • Projects • Variables • Transformation job • Orchestration job • Shared job • Schedules • Task history • API profiles • GIT • SSO • Email Notification (disable this when in development or test environments)
23 | Hand over to NPDC for any application level testing | NPDC | DONE | Qrious to assist NPDC for any application level testing questions 07 Feb: Connor has compared what upgraded Matillion produces on a few transformations against Prod and it looks identical, which along the testing Jianjun has done makes me confident everything is working as expected | NPDC SME to be available for Testing. | 4 | 2024-02-05
24 | Swap DNS between the original and new Matillion dev instances | NPDC | DONE | Qrious to perform network card change and validate its function 7-Feb: Confirmed from NPDC, this is now completed. | NPDC SME to standby for questions. |  | 2024-02-07
25 | Stop Matillion VM 1.68 | Manh | DONE | Qrious to perform shutdown of Matillion 1.68.7 VM | NPDC SME to standby for questions. |  | 2024-02-07
26 | Enable HTTPS on Matillion 1.72.4 | JJ | DONE | Qrious to configure Matillion 1.72.4 HTTPS | NPDC SME to standby for questions. Waiting for certificate from NPDC (c/o Sean) |  |  |  | https://docs.matillion.com/metl/docs/9483725/
27 | Restore Matillion VM shutdown policy (5pm to 7am) | Manh | DONE | Qrious to deploy this for NPDC
28 | Re-enable schedules in Matillion VM 1.72.4 | JJ | DONE | Qrious to re-enable any scheduled jobs in Matillion Development in 1.72.4 07 Feb: JJ checked that there is only one scheduled job in Matillion development environment "Sensus water meter data - daily load". This scheduled job is DISABLED, therefore no action needed for this task. | NPDC SME to standby for questions. | 1 | 2024-02-07
29 | Test scheduled jobs works in Matillion VM 1.72 as expected | JJ | DONE | Qrious to test job scheduling functionality in Matillion 1.72.4 07 Feb: Refer to task | NPDC SME to standby for questions. | 4 | 2024-02-07
115
|  |  |  | https://sparknz.sharepoint.com/:x:/r/sites/QriousC/NPDC/_layouts/15/Doc.aspx?sourcedoc=%7B83BF60DB-B4A6-4C7C-A006-930ADEE1730D%7D&file=Deployment%20Plan%20-%20P4439%20NPDC%20TechOne%20and%20MDP.xlsx&action=default&mobileredirect=true | HEre's the sample run sheet that we did for NPDC Deployment Link.
Note on K3: Sharon Alabastro: https://ubiquity.atlassian.net/jira/software/projects/NPDCMAT/boards/367/timeline?selectedIssue=NPDCMAT-11
Note on K7: Sharon Alabastro: https://teams.microsoft.com/l/meetup-join/19%3ameeting_MjY1YWY1NjUtMzIxOC00M2U1LWFmM2MtZGZhZTI0OTkzMmVh%40thread.v2/0?context=%7b%22Tid%22%3a%22f6b3cec6-a862-4a40-9ab4-00d6e11e6f0f%22%2c%22Oid%22%3a%2202225355-d4e9-464e-be8f-abbb0132e94f%22%7d

## TST - DONE
NPDC Matillion Migration and Upgrade (TEST Environment) 1.68.7 to 1.72.4
Project Phases and Schedule |  |  | Status | QRIOUS Team |  | NPDC Team |  | Workflow - Jira Board:
Ph1: Planning - Ends Jan 26th |  |  | DONE | Managing Consultant: | Scott McKay <Scott.McKay@qrious.co.nz> | Project Sponsor: | Jan Holdt <Jan.Holdt@npdc.govt.nz> | Link Here
PH2: Migration to Dev Instance - Jan 29th to Feb 2nd, 2023 |  |  | In Progress | Delivery Lead: | Sharon Alabastro <Sharon.Alabastro@qrious.co.nz> | NPDC Project Manager: | Carrie Taylor <Carrie.Taylor@npdc.govt.nz>
Ph3: Migration to TEST and PROD - Feb 5th to 9th (Feb 12 - 16) |  |  | In Progress | Solutions Architect: | Sandeep Gainda <Sandeep.Gainda@qrious.co.nz> | IT Sponsor | Storm Newland <Storm.Newland@npdc.govt.nz>
Ph4: Testing, Handover, Documentation - Feb 19 - 23 |  |  | Not Started | Senior Consultant: | Jianjun Dai <Jianjun.Dai@qrious.co.nz> | Product Owner: | Sandra Street <Sandra.Street@npdc.govt.nz> | Communications Channel - Teams Chat
|  |  |  | Senior Consultant: | Kay Wu <Kay.Wu@qrious.co.nz> | Data Engineer: | Connor Crowley <Connor.Crowley@npdc.govt.nz> | Link here
|  |  |  | MSE Lead: | Gary Sin <Gary.Sin@qrious.co.nz> | Data Engineer: | Donna Jolly <Donna.Jolly@npdc.govt.nz>
Holidays: Jan 22, WLG Anniv ¦ Jan 29, AKL Anniv ¦Feb 6th, Waitangi Day |  |  |  | Senior Engineer: | Manh Hoang Ha ManhHoang.Ha@qrious.co.nz | Security and Architecture SME​​ | Sean de Jager <Sean.deJager@npdc.govt.nz>
TEST
Task# | Task | Owners | Status | Responsibilities / Expected Outcome |  | Effort / Duration (Hours) - DEV | Planned Completion Date | Completion Time | Comments or Next Sub-Actions (RACI) | LEARNINGS
|  |  |  | Qrious | NPDC
1 | Request Matillion Test environment access for JJ | JJ and NPDC | DONE | Contact NPDC to obtain Matillion Test environment access |  | 1 | 2024-02-09
2 | Review number of versions in Matillion and remove unnecessary ones | JJ and NPDC | DONE | Check the number of versions in the environment as it may affect migration process. 09 Feb: only one version found, no action required. | NPDC SME to standby for questions., and identify the unncessary versions | 1 | 2024-02-09 |  | Unnecessary versions may slow down the migration process (https://community.matillion.com/s/question/0D5Tm000002hj2CKAQ/migrating-matillion-etl-1598-to-1730-but-migrate-utility-gets-stuck-help)
3 | Advise NPDC data engineer that Matillion upgrade on Test will start. | JJ and NPDC | DONE | Qrious (Sharon) to inform NPDC. | NPDC SME to standby for questions. | 1 | 2024-02-14 |  | Communication will be shared via Teams Chat
4 | Confirm no Matillion jobs are running and Disable any scheduled Matillion jobs. | JJ and NPDC | DONE | Qrious needs to advise NPDC that this task will impact only the DEV environment, therefore the NPDC's "BAU" activities (PROD env) are still going to continue as usual. | 1. NPDC SME to standby for questions. 2. NPDC SME to inform Qrious of what these Matillion Jobs are (In the Matillion Hub). | Effort 1 Duration 72 | 2024-02-09
5 | Backup Matillion VM 1.68 | Manh | DONE | This is not dependent on any NPDC actions. |  | 4 | 2024-02-12
6 | Install new Matilion VM 1.72.4 | Manh | DONE | Qrious to inform NPDC when installation starts, and ends, and communicate the new VM IP Address. (IAC). There is no dependency with NPDC at this point so this task can commence. | NPDC SME to standby for questions. | 10 | 2024-02-12
6.1 | Change Matillion VM 1.72.4 password for azure-user | Manh | DONE | Qrious to inform NPDC when this is done. | NPDC SME to standby for questions.
6.2 | Make sure the TCP/IP connection from Matillion VM 1.68 to Matillion VM 1.72 works | Manh | DONE | Manh to confirm with JJ. | NPDC SME to standby for questions.
6.3 | Make sure Matillion VM 1.72 is able to access artifacts.matillion.com | Manh | DONE | Manh to confirm with JJ. | NPDC SME to standby for questions.
6.4 | Whitelist IPs address to port 443 and 22 | Manh | DONE | This is to allow Qrious users to access the VM |  |  | 2024-02-12
6.5 | Setup SSO for the new Matillion | Manh / NPDC | DONE | Set up SSO for Matillion 1.72.4 | NPDC SME to standby for questions/ actions / access provision. |  | 2024-02-13
6.6 | Associate Matillion instance to Matillion hub account | JJ / NPDC | DONE | To add the new Matillion 1.72.4 instance to Matillion Hub |  | 1 | 2024-02-13
6.7 | Remove the instance shutdown restriction for both the 1.68.7 and 1.72.4 (currently between 5pm and 7am) in case if the migration process run over 5pm. | Manh | DONE | This is to allow long running jobs to be able to complete in the Matillion Test environment | NPDC SME to standby for questions. |  | 2024-02-13
6.8 | Assign the new Matillion VM to access adls storage account | Manh | DONE | In order to give new Matillion VM access to adls storage account, the old VM will need to be removed the access to storage account |  |  | 2024-02-13
6.9 | Add new Matillion VM IP address to whitelist to sendgrid firewall to allow it send email notification | Michael Okeeffe | DONE | This allows Matillion jobs to send email notifications
7 | Remove GIT from Matillion ETL 1.68.7 | JJ | DONE | This is to prepare for setting up GIT integration 19-Feb confirmed. GIT integration is removed. |  | 1 | 2024-02-14
8 | Go to Matillion VM 1.68, Admin -> Migrate and follow the prompts (TEST) | JJ | DONE | This is to migrate Matillion from 1.68.7 to 1.72.4 | NPDC SME to standby for questions. | 1 | 2024-02-14 |  | Follow the detail steps from https://docs.matillion.com/metl/docs/migration/#performing-the-migration Choose migrate with GIT Add screen shot of the configuration pages
9 | Configure GIT for Matillion 1.73.4 | JJ and NPDC | DONE | This is to configure GIT integration with Matillion | NPDC SME to standby for questions. | 2 | 2024-02-14
10 | Enable HTTPS on Matillion 1.72.4 | JJ | DONE | Qrious to configure Matillion 1.72.4 HTTPS. Replicate the .crt and .key file from the 1.68.7 VM to the 1.72.4 VM 14 Feb: Deployed the localhost.crt and localhost.key files from the old matillion test VM to the new matillion test VM. Need to wait for the DNS swap and restart the VM to take effect. | NPDC SME to standby for questions. Waiting for certificate from NPDC (c/o Sean) | 2 | 2024-02-14 |  | https://docs.matillion.com/metl/docs/9483725/
11 | Login to Matillion Test 1.72.4 and switch to default version and checkout test_master from GIT to get ready for batch run testing. | JJ | DONE | This is to create a workspace in the upgraded Matillion environment with the production set of the code to get ready for batch run testing. | NPDC SME to standby for questions. | 1 | 2024-02-14
12 | In Matillion VM 1.72, run all regularly scheduled workflows against TEST_DWH database. | JJ and NPDC | DONE | Qrious to execute the workflows to detect any issue. | NPDC SME to standby for questions. | 10 | 2024-02-14 |  | JJ - Unable to send email in the Test Instance. Need help from @Manh to investigate the cause. Sandeep to check if this was an issue in the DEV instance. |  | JJ - Also Observed in both the original Test Matillion (1.68) and the new Test Matillion (1.72), On-prem to ADLS File transfer step (smb://npdc.govt.nz;svc_matillion_user@10.115.12.14:445/SSIS_Data/MDP_DailyLoads/RAMM/corridor_access_requests.csv username svc_matillion_user) failed with error of unknow username or bad password, given it happens in both the original TEST and new TEST, it is unlikely an issue caused by upgrade, therefore, no further action to address it.
13 | Remediate errors and warnings as needed. | JJ and NPDC | DONE | Qrious to discuss with NPDC for any issues found during the job run and find solution for the remediation. | NPDC SME to standby for questions. | 2 | 2024-02-15 |  | JJ: NPDC have a job that goes through the matillion job history, however, it couldn't connect to this repository - unable to get this information. No issue when DEv upgrade was done. Sandeep to help JJ. |  | JJ - Test job is failing. JJ to check. (Sandra: Is OK if not to test). Sandeep - focus is for observations 1 and 2.
14 | Functional testing for Matllion VM 1.72: create user, create version, git integration, PVT | JJ | DONE | Qrious to test the Matilion VM 1.72.4 functions. | NPDC SME to standby for questions. | 4 | 2024-02-15 |  | These testing items may be: • User • Version • Transformation job as PVT • Orchestration job as PVT • Shared job • Schedules • Task history • GIT • SSO
15 | Hand over to NPDC for any application level testing | NPDC | DONE | Qrious to assist NPDC for any application level testing questions | NPDC SME to be available for Testing. | 4 | 2024-02-15
16 | Swap DNS to new VM | NPDC | DONE | Qrious to perform network card change and validate its function | NPDC SME to standby for questions. |  | 2024-02-15
17 | Stop Matillion VM 1.68 | Manh | DONE | Qrious to perform shutdown of Matillion 1.68.7 VM | NPDC SME to standby for questions. |  | 2024-02-15
18 | Restore Matillion VM shutdown policy (5pm to 7am) | Manh | DONE | Qrious to deploy this for NPDC |  |  | 2024-02-15
19 | If any, re-enable schedules in Matillion VM 1.72.4 | JJ | DONE | Qrious to re-enable any scheduled jobs in Matillion Test in 1.72.4 | NPDC SME to standby for questions. | 1 | 2024-02-15
20 | If any scheduled jobs, make sure they work in Matillion VM 1.72 as expected | JJ | DONE | Qrious to test job scheduling functionality in Matillion 1.72.4 | NPDC SME to standby for questions. | 4 | 2024-02-15
50
Note on J2: Sharon Alabastro: https://ubiquity.atlassian.net/jira/software/projects/NPDCMAT/boards/367/timeline?selectedIssue=NPDCMAT-11
Note on J6: Sharon Alabastro: https://teams.microsoft.com/l/meetup-join/19%3ameeting_MjY1YWY1NjUtMzIxOC00M2U1LWFmM2MtZGZhZTI0OTkzMmVh%40thread.v2/0?context=%7b%22Tid%22%3a%22f6b3cec6-a862-4a40-9ab4-00d6e11e6f0f%22%2c%22Oid%22%3a%2202225355-d4e9-464e-be8f-abbb0132e94f%22%7d

## PROD - DONE
NPDC Matillion Migration and Upgrade (PROD Environment) 1.68.7 to 1.72.4
Project Phases and Schedule |  |  | Status | QRIOUS Team |  | NPDC Team |  | Workflow - Jira Board:
Ph1: Planning - Ends Jan 26th |  |  | DONE | Managing Consultant: | Scott McKay <Scott.McKay@qrious.co.nz> | Project Sponsor: | Jan Holdt <Jan.Holdt@npdc.govt.nz> | Link Here
PH2: Migration to Dev Instance - Jan 29th to Feb 2nd, 2023 |  |  | DONE | Delivery Lead: | Sharon Alabastro <Sharon.Alabastro@qrious.co.nz> | NPDC Project Manager: | Carrie Taylor <Carrie.Taylor@npdc.govt.nz>
Ph3: Migration to TEST and PROD - Feb 5th to 9th (Feb 12 - 16) |  |  | DONE | Solutions Architect: | Sandeep Gainda <Sandeep.Gainda@qrious.co.nz> | IT Sponsor | Storm Newland <Storm.Newland@npdc.govt.nz>
Ph4: Testing, Handover, Documentation - Feb 12th to 23rd. |  |  | DONE | Senior Consultant: | Jianjun Dai <Jianjun.Dai@qrious.co.nz> | Product Owner: | Sandra Street <Sandra.Street@npdc.govt.nz> | Communications Channel - Teams Chat
|  |  |  | Senior Consultant: | Kay Wu <Kay.Wu@qrious.co.nz> | Data Engineer: | Connor Crowley <Connor.Crowley@npdc.govt.nz> | Link here
|  |  |  | MSE Lead: | Gary Sin <Gary.Sin@qrious.co.nz> | Data Engineer: | Donna Jolly <Donna.Jolly@npdc.govt.nz>
Holidays: Jan 22, WLG Anniv ¦ Jan 29, AKL Anniv ¦Feb 6th, Waitangi Day |  |  |  | Senior Engineer: | Manh Hoang Ha ManhHoang.Ha@qrious.co.nz | Security and Architecture SME​​ | Sean de Jager <Sean.deJager@npdc.govt.nz>
PROD
Task# | Task | Owners | Status | Responsibilities / Expected Outcome |  | Start Time | Planned Completion Time | Actual Completion Date | Comments or Next Sub-Actions (RACI) | LEARNINGS
|  |  |  | Qrious | NPDC
1 | Request Matillion PRODUCTION environment access for JJ | JJ and NPDC | DONE | Contact NPDC to obtain Matillion Production environment access |  | 2024-02-19 10:30 | 2024-02-19 15:30 | 2024-02-21 10:00
2 | Review number of versions in Matillion and remove unnecessary ones | JJ and NPDC | DONE | Check the number of versions in the environment as it may affect migration process. 21 Feb: only one version (default) found, no action required. | NPDC SME to standby for questions., and identify the unncessary versions |  |  | 2024-02-21 10:00 | Unnecessary versions may slow down the migration process (https://community.matillion.com/s/question/0D5Tm000002hj2CKAQ/migrating-matillion-etl-1598-to-1730-but-migrate-utility-gets-stuck-help)
3 | Backup Matillion VM 1.68 | Manh | DONE | This is not dependent on any NPDC actions. |  | 2024-02-22 13:00 | 2024-02-22 14:00
4 | Install new Matilion VM 1.72.4 | Manh | DONE | Qrious to inform NPDC when installation starts, and ends, and communicate the new VM IP Address. (IAC). There is no dependency with NPDC at this point so this task can commence. | NPDC SME to standby for questions. | 2024-02-21 09:00 | 2024-02-21 17:00
4.1 | Change Matillion VM 1.72.4 password for azure-user | Manh | DONE | Qrious to inform NPDC when this is done. | NPDC SME to standby for questions.
4.2 | Make sure the TCP/IP connection from Matillion VM 1.68 to Matillion VM 1.72 works | Manh | DONE | Manh to confirm with JJ. | NPDC SME to standby for questions.
4.3 | Make sure Matillion VM 1.72 is able to access artifacts.matillion.com | Manh | DONE | Manh to confirm with JJ. | NPDC SME to standby for questions.
4.4 | Whitelist IPs address to port 443 and 22 | Manh | DONE | This is to allow Qrious users to access the VM
4.5 | Setup SSO for the new Matillion | Manh / NPDC | DONE | Set up SSO for Matillion 1.72.4 | NPDC SME to standby for questions/ actions / access provision. - Estimate is 3PM
4.6 | Associate Matillion instance to Matillion hub account | JJ / NPDC | DONE | To add the new Matillion 1.72.4 instance to Matillion Hub | Estimate is 3PM | 2024-02-21 09:00 | 2024-02-21 17:00
4.7 | Remove the instance shutdown restriction for both the 1.68.7 and 1.72.4 (currently between 1700 and 0530) in case if the migration process run over 5pm. | Manh | DONE | This is to allow long running jobs to be able to complete in the Matillion Test environment | NPDC SME to standby for questions. | 2024-02-21 09:00 | 2024-02-21 17:00
4.8 | Assign the new Matillion VM to access adls storage account | Manh | DONE | In order to give new Matillion VM access to adls storage account, the old VM will need to be removed the access to storage account |  | 2024-02-21 09:00 | 2024-02-21 17:00 | 2024-02-20 15:00
4.9 | Add new Matillion VM IP address to whitelist to sendgrid firewall to allow it send email notification | Michael Okeeffe | DONE | This allows Matillion jobs to send email notifications |  |  |  | 2024-02-20 15:00
5 | Confirm no Matillion jobs are running and Disable any scheduled Matillion jobs. | JJ and NPDC | DONE | Qrious needs to advise NPDC that this task will impact only the DEV environment, therefore the NPDC's "BAU" activities (PROD env) are still going to continue as usual. | 1. NPDC SME to standby for questions. 2. NPDC SME to inform Qrious of what these Matillion Jobs are (In the Matillion Hub). | 22/02/2024 13:30:00 PM | 2024-02-22 14:15
6 | Advise NPDC data engineer that Matillion upgrade on PRODUCTION will start. | JJ and NPDC | DONE | Qrious (Sharon) to inform NPDC. | NPDC SME to standby for questions. | 2024-02-22 14:15 | 2024-02-22 14:30 |  | Communication will be shared via Teams Chat
7 | Remove GIT from Matillion ETL 1.68.7 | JJ | DONE | This is to prepare for setting up GIT integration |  | 2024-02-22 14:30 | 2024-02-22 15:00
8 | Go to Matillion VM 1.68, Admin -> Migrate and follow the prompts (PROD) | JJ | DONE | This is to migrate Matillion from 1.68.7 to 1.72.4 | NPDC SME to standby for questions. | 2024-02-22 15:00 | 2024-02-22 15:30 |  | Follow the detail steps from https://docs.matillion.com/metl/docs/migration/#performing-the-migration Choose migrate with GIT Add screen shot of the configuration pages
9 | Configure GIT for Matillion 1.73.4 | JJ and NPDC | DONE | This is to configure GIT integration with Matillion | NPDC SME to standby for questions. | 2024-02-22 15:30 | 2024-02-22 16:00
10 | Enable HTTPS on Matillion 1.72.4 | JJ | DONE | Qrious to configure Matillion 1.72.4 HTTPS. Replicate the .crt and .key file from the 1.68.7 VM to the 1.72.4 VM 22 Feb 10:08 Completed the upload of the crt and key file from the original linux VM to the new linux VM | NPDC SME to standby for questions. Waiting for certificate from NPDC (c/o Sean) | 2024-02-22 16:00 | 2024-02-22 16:30 |  | https://docs.matillion.com/metl/docs/9483725/
11 | Functional testing for Matllion VM 1.72: create user, create version, git integration, PVT | JJ | DONE | Qrious to test the Matilion VM 1.72.4 functions. | NPDC SME to standby for questions. | 2024-02-22 16:30 | 2024-02-22 17:00 |  | These testing items may be: • User • Version • Transformation job as PVT • Orchestration job as PVT • Shared job • Schedules • Task history • GIT • SSO
12 | Swap DNS to new VM | NPDC | DONE | Qrious to perform network card change and validate its function | NPDC SME to standby for questions. Estimate is between 5PM to 6PM (Actual swapping started at 3:39PM) | 2024-02-22 17:00 | 2024-02-22 17:30 |  | Feedback from Sean at 3:45PM - [3:45 PM] Sean de Jager Public DNS, Internal DNS and Firewall rules updated for prod.
13 | Stop Matillion VM 1.68 | Manh | DONE | Qrious to perform shutdown of Matillion 1.68.7 VM | NPDC SME to standby for questions. | 2024-02-22 17:30 | 2024-02-22 17:45
14 | Restore Matillion VM shutdown policy (5pm to 7am) | Manh | DONE | Qrious to deploy this for NPDC |  | 2024-02-22 17:30 | 2024-02-22 17:45
15 | Re-enable schedules in Matillion VM 1.72.4 | JJ | DONE | Qrious to re-enable any scheduled jobs in Matillion Production in 1.72.4 | NPDC SME to standby for questions. | 2024-02-22 17:45 | 2024-02-22 18:00
16 | Verify any scheduled jobs work correctly in Matillion VM 1.72 as expected | JJ | DONE | Qrious to verify scheduled job completed successfully in Matillion 1.72.4 | NPDC SME to standby for questions. | 2024-02-23 08:00 | 2024-02-23 09:00
17 | Remove old Matillion VM IP address from whitelist in sendgrid firewall (the IP is 4.196.145.69) | Michael Okeeffe | DONE | Remove old Matillion VM IP address from whitelist to sendgrid firewall (the IP is 4.196.145.69) |  | 2024-02-27 08:00
Rollback Plan
Task# | Task | Owners | Status | Responsibilities / Expected Outcome |  | Start Time | Planned Completion Time | Actual Completion Date | Comments or Next Sub-Actions (RACI)
|  |  |  | Qrious | NPDC
1 | Start Matillion VM 1.68.7 | Manh |  | Qrious to perform start of Matillion 1.68.7 VM
2 | Stop Matillion VM 1.72.4 | Manh |  | Qrious to perform shutdown of Matillion 1.72.4 VM
3 | Swap DNS to new VM | NPDC |  | Qrious to perform network card change and validate its function | NPDC SME to standby for questions.
4 | Verify Matillion VM 1.68.7 shutdown policy (5pm to 7am) | Manh |  | Check if shutdown policy is applied on Matillion VM 1.68.7 and apply if not in place. Qrious to deploy this for NPDC
5 | Verify jobs are scheduled in Matillion VM 1.68.7 | JJ |  | Qrious to re-enable any scheduled jobs in Matillion Production in 1.68.7 | NPDC SME to standby for questions.
6 | Verify any scheduled jobs work correctly in Matillion VM 1.68.7 as expected | JJ |  | Qrious to verify scheduled job completed successfully in Matillion 1.68.7 | NPDC SME to standby for questions.
Note on J2: Sharon Alabastro: https://ubiquity.atlassian.net/jira/software/projects/NPDCMAT/boards/367/timeline?selectedIssue=NPDCMAT-11
Note on J6: Sharon Alabastro: https://teams.microsoft.com/l/meetup-join/19%3ameeting_MjY1YWY1NjUtMzIxOC00M2U1LWFmM2MtZGZhZTI0OTkzMmVh%40thread.v2/0?context=%7b%22Tid%22%3a%22f6b3cec6-a862-4a40-9ab4-00d6e11e6f0f%22%2c%22Oid%22%3a%2202225355-d4e9-464e-be8f-abbb0132e94f%22%7d
Note on G33: Sharon Alabastro: Actual - [3:38 PM] Jianjun Dai Hi Sean de Jager (Guest), please proceed to the swap DNS task. [3:39 PM] Sean de Jager Going in... standby for confirmation [3:45 PM] Sean de Jager Public DNS, Internal DNS and Firewall rules updated for prod.

## IPs for Whitelisting
# | Name | IPs
1 | Qrious AKL Office | 146.171.246.81
2 | Qrious WLG Office | 146.171.247.81
3 | Jian Jun Dai (Home) | 27.252.188.138
4 | Sandeep Gainda (Home) | 60.234.115.77
5 | Manh Ha | 222.155.7.250
6 | Sharon Alabastro (Home) | 192.168.4.1
192.168.4.1

## Additional consideration
https://docs.matillion.com/metl/docs/migration/
Before you begin the process, consider the following factors.
A migration is not a 100% duplication of one instance into another. Ensure you have a working and tested migration strategy for features that don't get automatically migrated. The following resources will not be migrated:
Custom licences.
SSL certificates.
Task history.
Python libraries.
Non-standard JDBC drivers (click Admin in the top-right of the user interface, and then click Manage Database Drivers to view the list of database drivers that come with Matillion ETL "out of the box").
Customized "standard" API profiles.
LDAP setup.
Backend configuration changes (for example:
emerald.properties
file changes).
Git resources in versions of Matillion ETL prior to 1.61. See below for more details.
Local user configuration.